## M&E plan information
Column heading | Instructions
(*) Required Fields | Fields Items marked with an asterik (*) are required. Please ensure to complete these.
Output* (Expected results) | These are the results or change you would expect to occur immediately as a direct result of your activities. (e.g., # CHW trained, # of health campaigns, etc.)
Outcome* (Expected results) | These are the longer-term change you would expect of a group of people or institutions (e.g.,behaviour change, change the environment where they operate). Often outputs can contribute to outcomes.
Indicator* | Enter what is being counted or measured. Please be concise and clear.
Indicator definition* | Indicator definitions must clearly explain all terms and elements of the indicator to ensure consistent interpretation. Vague terms (e.g. “effective,” “quality,” “youth,” “vulnerable”) should be defined. Indicators that pertain to populations, geographic areas, or scores should include specified parameters or ranges. An equation or description of any calculations required to derive the data should be included. If the indicator is a percentage or ratio, include a description of the numerator and denominator.
Unit of measure* | Enter the unit of measure. Normally, the unit of measure should be either number (#) or percentage (%).
Disaggregated by* | List any planned ways of disaggregating the data (male/female, youth/adult, urban/rural, region, etc.).
Use of indicator* | Describe how this indicator will be used to monitor progress in achieving program outcomes.
Baseline #/% | If applicable, insert the measurement of conditions at the start of a project. All subsequent progress will be assessed against this starting point measurement. Some projects may need to plan to collect this at the start of their program.
Target #/%* | Insert the overall target to be reached by this indicator over the life of the program.
Data source* | Identify the documents, databases, organization, or individuals that will provide raw data for this indicator. Identify the source of data (e.g., department of health survey; ministry data; partner records). If data are from third-party sources such as a government ministry or international organization, include the citation or link to the source. If data are collected by implementing partners, specify where the partner is getting the data.
Data collection methods* | Describe the tools and methods for collecting the raw data (e.g., ledger of patient names, document review, structured interviews, focus group interviews, written survey, direct observation, self-reported information). If the indicator is an index or composite indicator, describe the procedure or formula for calculation.
Reporting frequency* | Specify how often data will be sent to Rotary and when. Most common reporting frequencies are quarterly, semiannual, and annual.
Responsibility for data collection* | Identify the person and position within each organization who will have responsibility for providing the data for the indicator.
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What else is useful to know?

## M&E plan_All Sites
DESCRIPTION |  |  | PLAN FOR DATA COLLECTION
Expected Results: Add/delete outcome and output lines as relevant to your program | Indicator* | Indicator definition* | Unit of measure* | Disaggregated by* | Use of indicator* | Baseline # and/or % | Year 1 | Year 2 | Year 3 | Total Milestones/Targets | Data Source* | Data collection method(s)* | Reporting frequency* | Responsibility for data collection*
Strategic Goal: To reduce severe disease and death due to Malaria, Pneumonia and Diarrhea in children under five through increased coverage and sustainable quality of care in RHCC districts
Primary Outcome 1 (a) Reduced deaths due to pneumonia, in children under five, in the RHCC districts | Mortality rate | - Numerator: # of pneumonia deaths - Denominator: # of children under 5 | Percentage | - Gender - Geography - Age | To track pneumonia deaths in under five children over time in a specified population/1000 | 3.59 | 2.5 | 1.5 | 1 | 0.5 | - National HMIS database - Facility registers/reports | Extraction from HMIS | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Mortality rate | - Numerator: # of diarrhea deaths - Denominator: # of children under 5 | Percentage | - Gender - Geography - Age | To track diarrhea deaths in under five children over time in a specified population/1000 | 0.19 | 0.01 | 0.008 | 0.005 | 0.002 | - National HMIS database - Facility registers/reports | Extraction from HMIS | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Mortality rate | - Numerator: # of malaria deaths - Denominator: # of children under 5 | Percentage | - Gender - Geography - Age | To track malaria deaths over time in a specified population/1000 | 0.22 | 0.12 | 0.08 | 0.06 | 0.04 | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Case Fatality Rate | # of deaths due to pneumonia per 1000 admissions of U5 in a given period | Percentage | - Gender - Geography - Age | To track severe pneumonia or the effectiveness of medical intervention | 28.8 | 20 | 12 | 8 | 5 | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Case Fatality Rate | # of deaths due to diarrhoea per 1000 admissions of U5 in a given period | Percentage | - Gender - Geography - Age | To track severe diarrhoea or the effectiveness of medical intervention | 15.65 | 11 | 8 | 6 | 3 | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Case Fatality Rate | # of deaths due to malaria per 1000 admissions of U5 in a given period | Percentage | - Gender - Geography - Age | To track severe malaria or the effectiveness of medical intervention | 52.18 | 35 | 20 | 10 | 5 | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
Primary outcome 1 (b): Reduced severe malaria in children under five in the RHCC districts | Incidence Rate | # of new severe malaria cases against the total population of U5 at risk in a specified period | Percentage | - Gender - Geography - Age | To track the incidence of severe malaria among the U5 children in the specified period | 4.19 | 3.5 | 3 | 2.5 | 2 | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | Quarterly/ Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Incidence Rate | # of new pneumonia cases against the total population of U5 at risk in a specified period | Percentage | - Gender - Geography - Age | To track the incidence of severe pneumonia among the U5 children in the specified period | 0.78 | 0.5 | 0.3 | 0.15 | 0.1 | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | Quarterly/ Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Incidence Rate | # of new severe diarrhea cases against the total population of U5 at risk in a specified period | Percentage | - Gender - Geography - Age | To track the incidence of severe diarrhoea among the U5 children in the specified period | 1.74 | 1.5 | 1.3 | 1.1 | 0.5 | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | Quarterly/ Semi-annually | - DHIO at district level - Facility in-charge at facility level
Intermediate Outcome 1.1 Increased access to malaria testing and treatment, and diarrhea and pneumonia services at community level | % of malaria cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | Percentage | - Gender - Geography - Age | Assesses the shift to community care | 0 | 25% | 50% | 70% | 80% | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of Pneumonia cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | Percentage | - Gender - Geography - Age | Assesses the shift to community care | 0 | 20% | 40% | 50% | 60% | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of diarrhoea cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | Percentage | - Gender - Geography - Age | Assesses the shift to community care | 0 | 30% | 60% | 80% | 90% | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of RHCC Health Facilities with no stockouts | Proportion of RHCCs with no stockouts of key supplies (RDTs, ACTs, Zinc, ORS, Amoxicillin) | Percentage | Commodity, District /Province, Reporting period | Assess stock availability at RHCCs [Used to assess the effectiveness of the supply chain, inventory management, and logistical systems that ensure the consistent availability of critical health supplies in rural health centers. It helps monitor whether the health facilities are able to serve the population effectively without interruptions due to supply shortages] | 0 | TBD | TBD | TBD | TBD | - National HMIS database - Facility registers/reports | Extraction from HMIS | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % CHWs who had no stock outs of commodities during the reporting period | # of CHWs who did not experience any stockouts of essential commodities in the reporting period./ The total number of CHWs who report on stock levels during the same period | Percentage | Commodity, Province/District | To monitor the progress of improving supply chain and distribution systems/ To measure the impact of interventions designed to reduce stockouts and improve access to essential commodities | 0 | TBD | TBD | TBD | TBD | - National HMIS database - Facility registers/reports | Extraction from HMIS | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Treatment coverage - malaria | Percentage of sick children who received timely and appropriate treatment for malaria - Numerator: # of under five children treated on time for malaria - Denominator: # of under five children diagnosed with malaria | Percentage | - Treatment point (health facility, CHW, etc) - Geography - Age - Gender | To enable assessment of the utilization of curative services for malaria within a given population. | 0 | TBD | TBD | TBD | TBD | - DHIS2 - HMIS - Household survey | - Extraction from HMIS/DHIS2 - Household survey interviews of mothers or caregivers | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Treatment coverage - Pneumonia | - Numerator: # of pneumonia cases treated at community level - Denominator: Total number of suspected under five pneumonia cases | Percentage | - Gender - Geography | To track the percentage of management of disease at community verses at faciity level | 0 | 30 | 50 | 70 | 70 | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Treatment coverage - diarrhea | Percentage of sick children who received timely and appropriate treatment for diarrhea - Numerator: # of under five children treated on time for diarrhea - Denominator: # of under five children diagnosed with diarrhea | Percentage | - Treatment point (health facility, CHW, etc) - Geography - Age - Gender | To enable assessment of the utilization of curative services for diarrhea within a given population. | 0 | TBD | TBD | TBD | TBD | - DHIS2 - HMIS - Household survey | - Extraction from HMIS/DHIS2 - Household survey interviews of mothers or caregivers | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of pnuemonia cases diagnosed at community level | - Numerator: # of under five pneumonia cases treated at community level - Denominator: Total number of suspected under five pneumonia cases | Percentage | - Gender - Geography | To track the percentage of management of disease at community verses at faciity level | 0 | 30 | 50 | 70 | 70 | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of diarrhea cases diagnosed at community level | - Numerator: # of under five diarrhea cases treated at community level - Denominator: Total number of suspected under five diarrhea cases | Percentage | - Gender - Geography | To track the percentage of management of disease at community verses at faciity level | 0 | 30 | 50 | 70 | 70 | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| % of malaria cases managed at community level | - Numerator: # of malaria cases treated at community level - Denominator: Total number of suspected malaria cases | Percentage | - Gender - Geography - Age | To track the percentage of management of disease at community verses at faciity level | 0 | 30 | 50 | 70 | 70 | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Proportion of CHWs who received at least one supervisory contact in the prior 3 months where registers were reviewed | # of CHWs who received at least one supervisory contact in the prior 3 month where registers were reviewed/ Total number of active CHWs | Percentage | Province/District/ Health facility | To track the frequency of supervisory visits and ensure they are occurring regularly/To assess the quality of supervision based on its focus on key areas like documentation, register management, and data accuracy. | 0 | 30 | 50 | 80 | 80 | Supervisory reports/Supervision logs or visit records/CHW self-reporting (e.g., surveys or interviews) | - Interviews - Physical checks | Quarterly | - DHIO at district level - Facility in-charge at facility level
| Proportion of CHWs who correctly count respiratory rate to diagnose ARI | # of CHWs who correctly count respiratory rate to diagnose ARI/ Total number assessed | Percentage | Province/District | The indicator tracks how well CHWs are applying their knowledge and skills in diagnosing ARI based on respiratory rate | 0 | 80 | 100 | 100 | 100 | MTSS reports/ District performance Assessment reports | - Interviews - Physical checks | Semi-annually | - DHIO at district level - Facility in-charge at facility level
| Proportion of sick children recommended for referral who are received at referral facility | # of sick children recommended for referral facility/ Total received at referral facility | Percentage | Gender, Age, Disease, Province/District | By tracking whether referred children receive care, the indicator helps to identify whether there are gaps in the continuum of care. Children who are recommended for referral but do not receive care at a referral facility may face complications due to delayed treatment. | 0 | 80 | 90 | 100 | 100 | Referral Records/Referral Logs at the Referral Facility/Health Information Management Systems | Extraction from HMIS/DHIS2 | Monthly | - DHIO at district level - Facility in-charge at facility level
Output 1.1.1 Community health worker (CHW) candidates selected by community leaders and neighbourhood health committees (NHCs) | # of CHWs selected with community involvement | CHWs selected through local leadership in respective zones | Number | - Gender - Geography | To track involvement of community leadership in the selection of CHWs | 0 | 2086 | 0 | 0 | 2086 | - Pre-selection registers | - Interviews - Physical checks | Semi-annually | - DHIO at district level - EHO at district level - Facility in-charge at facility level
Output 1.2.1 (a) CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines | # of CHWs trained | CHWs trained to test, treat, track and refer malaria, diarrhea and pneumonia cases | Number | - Gender - Geography | To track the number of CHWs equipped with skills to manage diarrhea, pneumonia and malaria | 0 | 1043 | 1043 |  | 2086 | - Training attendance registers | - Physical checks | Semi-annually | - Project - MoH
Output 1.2.1 (b) CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines deployed | # of CHWs deployed | CHWs deployed | Number | - Gender - Geography | To track the number of CHWs equipped and deployed with skills to manage diarrhea, pneumonia and malaria | 0 | 1043 | 1043 |  | 2086
Output 1.1.3 CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines | # of health facility supervisors trained | Health facility supervisors trained to test, treat, track and refer malaria, diarrhea and pneumonia cases | Number | - Gender - Geography | To track the number of health facility supervisors equipped with skills to manage diarrhea, pneumonia and malaria | 0 | 81 | 82 | 0 | 163 | - Training attendance registers | - Physical checks | Semi-annually | - Project - MoH
Output 1.3.1 (a) CHWs equipped with a starter pack (incentives) and consistent supply of commodities to diagnose and treat disease at community level | # of CHWs equipped with starter packs | CHWs provided with minimum set of starter pack items per NMEC standard | Number | - Gender - Geography | To track the number of CHWs equipped with enablers to manage diarrhea, pneumonia and malaria | 0 | 1043 | 1043 | 0 | 2086 | - Training attendance registers - Started pack supply register | - Physical checks | Semi-annually | - Project - MoH
Output 1.3.1 (b) CHWs equipped with a starter pack (incentives) and consistent supply of commodities to diagnose and treat disease at community level | # of CHWs with consistent supply of commodities to diagnose and treat disease at community level | CHWs provided with supply of commodities to diagnose and treat disease | Number | - Gender - Geography | To track the number of CHWs equipped with enablers to manage diarrhea, pneumonia and malaria | 0 | 1043 | 1043 | 0 | 2086 | - Training attendance registers - Started pack supply register | - Physical checks | Semi-annually | - Project - MoH
Intermediate Outcome: Increased community awareness and demand for malaria, diarrhea, and pneumonia prevention and treatment services | Proportion of caregiver knowledge of CHW location and role | Proportion of caregivers in target areas who know of the presence and role of their CHW | Percentage | - Geography | To measure effectiveness of communication and community sensitization around iCCM | 0 | 100 | 100 | 100 | 100 | - Household survey | - Household survey interviews of mothers or caregivers | Episodic | - Project - MoH
| % of community members aware of iCCM services | Population aware of iCCM services | Percentage | - Gender - Geography - Age | To determine community knowledge about the availability of iCCM services in RHCC districts | 0 | 40 | 60 | 90 | 90 | - Survey - CCAs' reports | - FGDs - KIIs | Annually | - Project - MoH
| % of community members seeking iCCM services | Population seeking iCCM services | Percentage | - Gender - Geography - Age | To determine the demand for iCCM services in RHCC districts | 0 | 50 | 60 | 70 | 70 | - Survey - CCAs' reports | - FGDs - KIIs | Annually | - Project - MoH
Output 1.4.1 CHWs oriented in interpersonal communication (IPC) to conduct community sensitization and mobilization | # of CHWs oriented | CHWs oriented to conduct community malaria , pneumonia and diarrhea awareness activities | Number | - Gender - Geography | To determine the spread of IPC-oriented CHWs in health facility catchment areas | 0 | 1043 | 1043 | 0 | 2086 | - Training attendance registers | - Physical checks | Semi-annually | - Project - MoH
| Number of radio adverts aired | The total number of radio adverts broadcasted as part of the community sensitization efforts | Number | Geography | To track the extent of radio outreach in raising awareness about community health and mobilization efforts. | 0 | 6 | 6 | 6 | 18 | Activity reports | - Physical checks | Semi-annually | - Project - MoH
| Number of radio talk shows conducted | The total number of radio talk shows featuring health topics that involve CHWs and encourage community participation. | Number | Geography | To measure the engagement and dissemination of health-related information through interactive discussions | 0 | 72 | 72 | 72 | 216 | Activity reports | - Physical checks | Semi-annually | - Project - MoH
| Number of signage materials deployed | The total number of signage materials, such as pop-ups and backdrops, used for sensitization in public spaces. | Number | Geography | To track the visibility and presence of health messages in key community areas and ensure wide public exposure. | 0 | 4 | 4 |  | 8 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of billboards placed | The total number of billboards placed in strategic locations for public health messaging. | Number | Geography | To measure the scale of billboard usage for promoting health messages across different locations in the community | 0 | 6 | 0 |  | 6 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of offices branded with materials created | The total number of branding materials (such as posters, logos, or banners) displayed in project offices. | Number | Geography | To evaluate the internal visibility and consistency of the health messages within project-related spaces. | 0 | 2 |  |  | 2 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of posters produced and distributed | The total number of posters produced and distributed for community sensitization on health topics. | Number | Geography | To measure the production and distribution reach of printed health communication materials in the community. | 0 | 163 |  |  | 163 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
Output 1.4.2 Communities supported with information and educational messages on WASH | Number of Community/School Lead Sanitation Facilitators trained | The total number of facilitators trained in Total Sanitation (community and school). | Number | Geography | To track the capacity building of community and school-based facilitators who will lead WASH efforts. | 0 | 163 |  |  | 163 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of districts where CLTS is conducted | The total number of districts where the CLTS methodology was implemented to trigger community-led sanitation efforts. | Number | Geography | To measure the geographical coverage and impact of CLTS activities in promoting improved sanitation in the community. | 0 | 6 |  |  | 6 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of districts where SLTS is conducted | The total number of districts where SLTS programs are implemented, focusing on school sanitation and hygiene. | Number | Geography | To assess the number of school-based sanitation programs conducted to ensure clean and safe school environments. | 0 | 6 |  |  | 6 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
| Number of communities declared ODF | The total number of communities that have been certified as open defecation-free as a result of sanitation programs. | Number | Geography | To measure the success of sanitation initiatives and the effectiveness of community efforts in eliminating open defecation. | 0 | 10 |  |  | 10 | Activity reports/ | - Physical checks | Semi-annually | - Project - MoH
Primary Outcome 2 Strengthened and sustainable community health systems
Intermediate Outcome 2.1 Timely, accurate, and complete surveillance data being reported from RHCC districts. | % of surveillance reports submitted on time | - Numerator: Number of surveillance reports submitted on time - Denominator: Expected number of surveillance reports | Percentage | - Georgraphy - Month | To determine the proportion of reports submitted on time for timely decision making | 0 | 95 | 95 | 95 | 95 | - DHIS2 - Tableau | - Monthly data reviews | Semi-annually | - Project - MoH (Malaria Elimination Officers)
| % of accurate surveillance reports submitted | - Numerator: Number of accurate surveillance reports submitted - Denominator: Expected number of surveillance reports | Percentage | - Georgraphy - Month | To determine what proportion of submitted reports are accurate for informed decision making | 0 | 80 | 90 | 95 | 95 | - CHW passive and active registers - Health facility registers | - Monthly data reviews - Data quality audits - MTSS | Semi-annually | - Project - MoH (Malaria Elimination Officers)
| % of complete surveillance reports submitted | - Numerator: Number of complete surveillance reports submitted - Denominator: Expected number of surveillance reports | Percentage | - Georgraphy - Month | To determine what proportion of submitted reports are accurate for informed decision making | 0 | 80 | 90 | 95 | 95 | - DHIS2 - Tableau | - Monthly data reviews | Semi-annually | - Project - MoH (Malaria Elimination Officers)
Output 2.1.1 CHWs equipped with skills on reporting and use of iCCM disease data | # of data CHWs trained | CHWs trained to report on and make decisions from iCCM disease data | Number | - Gender - Geography | To determine the number of CHWs equipped with skills to report iCCM data and make decisions from it | 0 | 149 | 149 | 0 | 298 | - Training attendance registers | - Physical checks | Semi-annually | - Project - MoH
Output 2.1.2 Health facility officers equipped with skills in reporting facility data on iCCM diseases and supply chain | # of health facility staff trained | Health facility staff trained to report iCCM disease and supply chain data | Number | - Gender - Geography | To determine the number of health facility staff equippped with skills to report iCCM disease and supply chain data | 0 | 81 | 82 | 0 | 163 | - Training attendance registers | - Physical checks | Semi-annually | - Project - MoH
Output 2.1.4 Data Quality Audit to CHW's Community level inclusive NHC selected members conducted | # of Data Quality Audit conducted | # Data Quality Audit conducted | Number | Geography | To determine the number of Data Quality audit conducted out of the planned | 0 | 0 | 1 | 1 | 2 | Data quality audit report | - Physical checks | Annually | - Project
Output 2.1.6 MTSS to CHW's (mentorship and technical supportive supervision) conducted at community and faciity level | # of MTSS to CHW's conducted | # of MTSS to CHW's conducted | Number | Geography | To determine the number of MTSS conducted to CHW's out of the planned | 0 | 0 | 1 | 1 | 2 | MTSS reports | - Physical checks | Annually | - Project
| # of CHWs who received at least one supervisory contact in the prior 3 months where registers were reviewed | # of CHWs who received at least one supervisory contact in the prior 3 month where registers were reviewed | Number | Province/District/ Health facility | To track the frequency of supervisory visits and ensure they are occurring regularly/To assess the quality of supervision based on its focus on key areas like documentation, register management, and data accuracy. | 0 | 0 | 1043 | 1043 | 2086 | Supervisory reports/Supervision logs or visit records/CHW self-reporting (e.g., surveys or interviews) | - Physical checks/ Extraction from RHCC reporting system | Quarterly | - Project - MoH
| # of CHWs who correctly count respiratory rate to diagnose ARI | # of CHWs who correctly count respiratory rate to diagnose ARI | Number | Province/District | The indicator tracks how well CHWs are applying their knowledge and skills in diagnosing ARI based on respiratory rate | 0 | 0 | 1043 | 1043 | 2086 | MTSS reports/ District performance Assessment reports | Physical assessment/Spot checks | Semi-annually | - Project - MoH
| # of sick children recommended for referral who are received at referral facility | # of sick children recommended for referral facility | Number | Gender, Age, Disease, Province/District | To track the effectiveness of the referal system | 0 | 0 | TBD | TBD | TBD | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from DHIS2 | Monthly
| # of CHWs who are providing iCCM services one year after deployment | # of CHWs who are providing iCCM services one year after deployment | Number | Province/District | To track active CHWs providing ICCM services after deployment | 0 |  | 1043 |  | 2086 | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from DHIS2 | Annually
Intermediate Outcome 2.2 Increased number of Ministry of Health staff competent in use of digitised tools | Proportion of iCCM supervisor trained | Numerator: # of supervisors assigned to iCCM (at all levels of the health system) that have been trained in iCCM Denominator: # of supervisors assigned to iCCM (at all levels of the health system) | Percentage | Gender Geography | To measure Proportion of health facility staff assigned to iCCM that were trained in iCCM | 0 | 81 | 8212 | 100 | 100 | - Training attendance registers - Surveys | - Physical checks - Key informant interviews | Annual | - Project - MoH
Output 2.3.1 Integrated tools for tracking Malaria, Pneumonia and Diarrhea developed | # of disease specific tracked | Monthly data tracked for all three diseases | Number | - Gender - Geography - Age | To detemine malaria, pneumonia and diarrhea are being tracked reliably in a single platform | 0 | TBD | TBD | TBD | TBD | DHIS2 | Extraction from DHIS2 | Monthly | - Project - NMEC SMEOR Unit
| # of CHW and facility phones procured | Tracking of mobile phones procured | Number | Geography | T assess the number procured against the planned | 0 | 266 | 0 | 0 | 266 | Inventory, | - Physical checks | Monthly | - Project - NMEC SMEOR Unit
Intermediate Outcome 3.1 Improved advocacy and resource mobilization in RHCC districts | # of Rotarians participating in advocacy and resource mobilisation activities in RHCC districts | Number of Rotarians who participated in advocacy and resource mobilization for iCCM interventions in RHCC districts | Number | Gender Geography | To determine how many Rotarians are participating in project activities | 0 | 100 | 100 | 100 | TBD | Training attendance registers | - Monthly data reviews | Semi-annually | - Project
Output 3.1.2: Rotarians and RHCC Country Committee participate in Global Fund commodity stakeholder meetings | Medicine and diagnostic availability | Percentage of iCCM sites with all key iCCM medicines and diagnostics in stock during the last day of reporting period Numerator: # of iCCM sites with all key iCCM medicines and diagnostics in stock during the last day of a reporting period. Denominator: # of iCCM sites assessed | Percentage | Geography | To determine to what extent iCCM diagnostic and treatment products are available at a given point in time | 0 | 100 | 100 | 100 | 100 | - DHIS2 | - Extraction from DHIS2 | Semi-annually | Project
| # of policy dialogues attended | # of policy dialogue attended to secure commitments for CHW integration and continued supply of commodities | Number | Geography | To secure commitments for CHW integration, and continued supply of commodities | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical checks | Semi-annually | Project
| # of Rotarians participating in stakeholder meetings | Number of Rotarians participating in National Malaria Elimination Programme meetings | Number | Geography | To determine the involvement of Rotarians in Global Fund meetings to influence funding for iCCM interventions | 0 | 12 | 12 | 12 | 36 | - Training attendance registers | - Physical checks | Semi-annually | Project
Output 3.1.4 Rotary represented on provincial-level End Malaria Councils to leverage private sector support | # of subnational End Malaria Council with rotarian representations in RHCC sites | # of subnational End Malaria Council with rotarian representations in RHCC sites | Number | Province/ district | To determine the proportion of participation of rotarian in End Malaria Council in RHCC sites | 0 | 2 | 2 | 2 | 2 | Reports, minutes | Physical checks | Semi-annually | Project
Output 3.1.7: Rotarians trained in the Alma Scorecard for Surveillance & Data Monitoring | # of rotarians trained | # of Rotarians Trained | Number | Geography | To track the number of Rotarian representation trained in RHCC sites | 0 | TBD | TBD | TBD | TBD | - DHIS2 | - Extraction from DHIS2 | Semi-annually | Project
| Proportion of surveillance reports generated by trained Rotarians | # of surveillance reports generated/ The expected | Percentage | Geography | To track Rotarian surveillance activities in RHCC sites | 0 | TBD | TBD | TBD | TBD | - DHIS2 | - Extraction from DHIS2 | Semi-annually | Project
Output 3.1.8: Advocacy members trained in RHCC | # of Advocacy members trained | # of Advocacy members trained in RHCC | Number | Geography | To build the foundational capacity of the RHCC Advocacy Committee on key advocacy strategies, stakeholder engagement, and policy influence. | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical checks | Semi-annually | Project
| # of Rotary President-Elects (PEs) trained on Advocacy and RHCC | Number of Rotary President-Elects (PEs) trained on Advocacy and RHCC | Number | Geography | To expand advocacy leadership within Rotary by equipping all President-Elects of | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical checks | Semi-annually | Project
| # of advocacy activities initiated by trained members | Number of activities initiated by trained members | Number | Geography | To track advocacy activities initiated by trained members | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical assessment/Spot checks | Semi-annually | Project
Output 3.1.6: Participated in National Campaigns and Rotary Family Health Days | # of National Campaigns campaigns participated by rotarians | Number of campaigns participated Total held | Number | Geography | To track Rotary and Rotaract Clubs with knowledge on RHCC and advocacy strategies. | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical assessment/Spot checks | Semi-annually | Project
| # of family health days participated by rotarians | Number of family health days participat | Number | Geography | To track rotarian participation in rotary family health days | 0 | TBD | TBD | TBD | TBD | Reports, minutes | Physical assessment/Spot checks | Semi-annually | Project
Note on G18: Wongani Zulu: No CHWs have been trained yet
Note on G23: Wongani Zulu: No CHWs have been trained yet
Note on G25: Wongani Zulu: TBD
Note on L25: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on G38: Wongani Zulu: No iCCM+-trained CHWs exist yet
Note on L38: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on N38: Wongani Zulu: To only be reported when data is collected
Note on K64: Wongani Zulu: All supervisors assigned to mentor CHWs in iCCM+ should have been trained prior to their assignement as supervisors
Note on G68: Wongani Zulu: Yet to be determined

## Results framework_New
DESCRIPTION
Expected Results: Add/delete outcome and output lines as relevant to your program | Indicator* | Indicator definition* | Data Source* | Data collection method(s)* | Baseline # and/or % | Year 1 | Year 2 | Year 3 | Total Milestones/Targets | Qtr 1 & 2 2025 Achievement | Qtr 3 & 4 2025 Achievement | Overall Achievement | Explanation for variance
Strategic Goal: To reduce severe disease and death due to Malaria, Pneumonia and Diarrhea in children under five through increased coverage and sustainable quality of care in RHCC districts
Primary Outcome 1 (a) Reduced deaths due to pneumonia, in children under five, in the RHCC districts | Mortality rate | - Numerator: # of pneumonia deaths - Denominator: # of children under 5 | - National HMIS database - Facility registers/reports | Extraction from HMIS | #REF! | 2.5 | 1.5 | 1 | 0.5 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Mortality rate | - Numerator: # of diarrhea deaths - Denominator: # of children under 5 | - National HMIS database - Facility registers/reports | Extraction from HMIS | #REF! | 0.01 | 0.008 | 0.005 | 0.002 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Mortality rate | - Numerator: # of malaria deaths - Denominator: # of children under 5 | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from HMIS/DHIS2 | #REF! | 0.12 | 0.08 | 0.06 | 0.04 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Case Fatality Rate | # of deaths due to pneumonia per 1000 admissions of U5 in a given period | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | #REF! | 20 | 12 | 8 | 5 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Case Fatality Rate | # of deaths due to diarrhoea per 1000 admissions of U5 in a given period | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | #REF! | 11 | 8 | 6 | 3 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Case Fatality Rate | # of deaths due to malaria per 1000 admissions of U5 in a given period | Facility IPD Register, HMIS, DHIS2 | Extraction from HMIS/DHIS2 | #REF! | 35 | 20 | 10 | 5 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Primary outcome 1 (b): Reduced severe malaria in children under five in the RHCC districts | Incidence Rate | # of new severe malaria cases against the total population of U5 at risk in a specified period | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | #REF! | 3.5 | 3 | 2.5 | 2 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Incidence Rate | # of new pneumonia cases against the total population of U5 at risk in a specified period | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | #REF! | 0.5 | 0.3 | 0.15 | 0.1 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Incidence Rate | # of new severe diarrhea cases against the total population of U5 at risk in a specified period | - National HMIS database - Facility registers/reports | MRR system, HMIS, Zambia DHIS2 | #REF! | 1.5 | 1.3 | 1.1 | 0.5 |  |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Intermediate Outcome 1.1 Increased access to malaria testing and treatment, and diarrhea and pneumonia services at community level | % of malaria cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | 0 | 25% | 50% | 70% | 80% | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of Pneumonia cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | 0 | 20% | 40% | 50% | 60% | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of diarrhoea cases managed at community vs health facility | Proportion of cases managed at community vs health facility level - [Proportion of cases managed at the community level relative to those managed at the health facility level. It is a comparison of the number of cases treated or managed in the community (by community health workers or community-based health initiatives) versus those that are referred to or managed in health facilities (clinics, hospitals). | - CHW survey - Household survey - CHW registers | - Extraction from HMIS/DHIS2 - Interviews | 0 | 30% | 60% | 80% | 90% | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of RHCC Health Facilities with no stockouts | Proportion of RHCCs with no stockouts of key supplies (RDTs, ACTs, Zinc, ORS, Amoxicillin) | - National HMIS database - Facility registers/reports | Extraction from HMIS | 0 | TBD | TBD | TBD | TBD | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % CHWs who had no stock outs of commodities during the reporting period | # of CHWs who did not experience any stockouts of essential commodities in the reporting period./ The total number of CHWs who report on stock levels during the same period | - National HMIS database - Facility registers/reports | Extraction from HMIS | 0 | TBD | TBD | TBD | TBD | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Treatment coverage - malaria | Percentage of sick children who received timely and appropriate treatment for malaria - Numerator: # of under five children treated on time for malaria - Denominator: # of under five children diagnosed with malaria | - DHIS2 - HMIS - Household survey | - Extraction from HMIS/DHIS2 - Household survey interviews of mothers or caregivers | 0 | TBD | TBD | TBD | TBD | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Treatment coverage - Pneumonia | - Numerator: # of pneumonia cases treated at community level - Denominator: Total number of suspected under five pneumonia cases | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | 0 | 30 | 50 | 70 | 70 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Treatment coverage - diarrhea | Percentage of sick children who received timely and appropriate treatment for diarrhea - Numerator: # of under five children treated on time for diarrhea - Denominator: # of under five children diagnosed with diarrhea | - DHIS2 - HMIS - Household survey | - Extraction from HMIS/DHIS2 - Household survey interviews of mothers or caregivers | 0 | TBD | TBD | TBD | TBD | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of pnuemonia cases diagnosed at community level | - Numerator: # of under five pneumonia cases treated at community level - Denominator: Total number of suspected under five pneumonia cases | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | 0 | 30 | 50 | 70 | 70 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of diarrhea cases diagnosed at community level | - Numerator: # of under five diarrhea cases treated at community level - Denominator: Total number of suspected under five diarrhea cases | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | 0 | 30 | 50 | 70 | 70 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of malaria cases managed at community level | - Numerator: # of malaria cases treated at community level - Denominator: Total number of suspected malaria cases | - National DHIS2 database - National HMIS database | Extraction from HMIS/DHIS2 | 0 | 30 | 50 | 70 | 70 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Proportion of CHWs who received at least one supervisory contact in the prior 3 months where registers were reviewed | # of CHWs who received at least one supervisory contact in the prior 3 month where registers were reviewed/ Total number of active CHWs | Supervisory reports/Supervision logs or visit records/CHW self-reporting (e.g., surveys or interviews) | - Interviews - Physical checks | 0 | 30 | 50 | 80 | 80 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Proportion of CHWs who correctly count respiratory rate to diagnose ARI | # of CHWs who correctly count respiratory rate to diagnose ARI/ Total number assessed | MTSS reports/ District performance Assessment reports | - Interviews - Physical checks | 0 | 80 | 100 | 100 | 100 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Proportion of sick children recommended for referral who are received at referral facility | # of sick children recommended for referral facility/ Total received at referral facility | Referral Records/Referral Logs at the Referral Facility/Health Information Management Systems | Extraction from HMIS/DHIS2 | 0 | 80 | 90 | 100 | 100 | N/A |  | N/A | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.1.1 Community health worker (CHW) candidates selected by community leaders and neighbourhood health committees (NHCs) | # of CHWs selected with community involvement | CHWs selected through local leadership in respective zones | - Pre-selection registers | - Interviews - Physical checks | 0 | 2086 | 0 | 0 | 2086 | 2086 |  | 1214 | CHWs selection is a once off activity as such the target is 2086 for the entire project. In the period under review, 1214 CHWs were selected from 3 out of 6 districts.
Output 1.2.1 (a) CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines | # of CHWs trained | CHWs trained to test, treat, track and refer malaria, diarrhea and pneumonia cases | - Training attendance registers | - Physical checks | 0 | 1043 | 1043 |  | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.2.1 (b) CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines deployed | # of CHWs deployed | CHWs deployed |  |  | 0 | 1043 | 1043 |  | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.1.3 CHWs trained with their health facility supervisor to test, treat and track malaria, diarrhea and pneumonia, and to refer patients per MOH guidelines | # of health facility supervisors trained | Health facility supervisors trained to test, treat, track and refer malaria, diarrhea and pneumonia cases | - Training attendance registers | - Physical checks | 0 | 81 | 82 | 0 | 163 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.3.1 (a) CHWs equipped with a starter pack (incentives) and consistent supply of commodities to diagnose and treat disease at community level | # of CHWs equipped with starter packs | CHWs provided with minimum set of starter pack items per NMEC standard | - Training attendance registers - Started pack supply register | - Physical checks | 0 | 1043 | 1043 | 0 | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.3.1 (b) CHWs equipped with a starter pack (incentives) and consistent supply of commodities to diagnose and treat disease at community level | # of CHWs with consistent supply of commodities to diagnose and treat disease at community level | CHWs provided with supply of commodities to diagnose and treat disease | - Training attendance registers - Started pack supply register | - Physical checks | 0 | 1043 | 1043 | 0 | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Intermediate Outcome: Increased community awareness and demand for malaria, diarrhea, and pneumonia prevention and treatment services | Proportion of caregiver knowledge of CHW location and role | Proportion of caregivers in target areas who know of the presence and role of their CHW | - Household survey | - Household survey interviews of mothers or caregivers | 0 | 100 | 100 | 100 | 100 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of community members aware of iCCM services | Population aware of iCCM services | - Survey - CCAs' reports | - FGDs - KIIs | 0 | 40 | 60 | 90 | 90 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of community members seeking iCCM services | Population seeking iCCM services | - Survey - CCAs' reports | - FGDs - KIIs | 0 | 50 | 60 | 70 | 70 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.4.1 CHWs oriented in interpersonal communication (IPC) to conduct community sensitization and mobilization | # of CHWs oriented | CHWs oriented to conduct community malaria , pneumonia and diarrhea awareness activities | - Training attendance registers | - Physical checks | 0 | 1043 | 1043 | 0 | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of radio adverts aired | The total number of radio adverts broadcasted as part of the community sensitization efforts | Activity reports | - Physical checks | 0 |  |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of radio talk shows conducted | The total number of radio talk shows featuring health topics that involve CHWs and encourage community participation. | Activity reports | - Physical checks | 0 |  |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of signage materials deployed | The total number of signage materials, such as pop-ups and backdrops, used for sensitization in public spaces. | Activity reports/ | - Physical checks | 0 |  |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of billboards placed | The total number of billboards placed in strategic locations for public health messaging. | Activity reports/ | - Physical checks | 0 | 6 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of offices branded with materials created | The total number of branding materials (such as posters, logos, or banners) displayed in project offices. | Activity reports/ | - Physical checks | 0 | 2 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of posters produced and distributed | The total number of posters produced and distributed for community sensitization on health topics. | Activity reports/ | - Physical checks | 0 | 163 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 1.4.2 Communities supported with information and educational messages on WASH | Number of Community/School Lead Sanitation Facilitators trained | The total number of facilitators trained in Total Sanitation (community and school). | Activity reports/ | - Physical checks | 0 | 163 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of districts where CLTS is conducted | The total number of districts where the CLTS methodology was implemented to trigger community-led sanitation efforts. | Activity reports/ | - Physical checks | 0 | 6 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of districts where SLTS is conducted | The total number of districts where SLTS programs are implemented, focusing on school sanitation and hygiene. | Activity reports/ | - Physical checks | 0 | 6 |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| Number of communities declared ODF | The total number of communities that have been certified as open defecation-free as a result of sanitation programs. | Activity reports/ | - Physical checks | 0 |  |  |  |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Primary Outcome 2 Strengthened and sustainable community health systems
Intermediate Outcome 2.1 Timely, accurate, and complete surveillance data being reported from RHCC districts. | % of surveillance reports submitted on time | - Numerator: Number of surveillance reports submitted on time - Denominator: Expected number of surveillance reports | - DHIS2 - Tableau | - Monthly data reviews | 0 | 80 | 90 | 95 | 95 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of accurate surveillance reports submitted | - Numerator: Number of accurate surveillance reports submitted - Denominator: Expected number of surveillance reports | - CHW passive and active registers - Health facility registers | - Monthly data reviews - Data quality audits - MTSS | 0 | 80 | 90 | 95 | 95 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| % of complete surveillance reports submitted | - Numerator: Number of complete surveillance reports submitted - Denominator: Expected number of surveillance reports | - DHIS2 - Tableau | - Monthly data reviews | 0 | 80 | 90 | 95 | 95 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 2.1.1 CHWs equipped with skills on reporting and use of iCCM disease data | # of data CHWs trained | CHWs trained to report on and make decisions from iCCM disease data | - Training attendance registers | - Physical checks | 0 |  |  | 0 | 0 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 2.1.2 Health facility officers equipped with skills in reporting facility data on iCCM diseases and supply chain | # of health facility staff trained | Health facility staff trained to report iCCM disease and supply chain data | - Training attendance registers | - Physical checks | 0 | 81 | 82 | 0 | 163 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 2.1.4 Data Quality Audit to CHW's Community level inclusive NHC selected members conducted | # of Data Quality Audit conducted | # Data Quality Audit conducted | Data quality audit report | - Physical checks | 0 | 0 | 1 | 1 |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Output 2.1.6 MTSS to CHW's (mentorship and technical supportive supervision) conducted at community and faciity level | # of MTSS to CHW's conducted | # of MTSS to CHW's conducted | MTSS reports | - Physical checks | 0 | 0 | 1 | 1 |  | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| # of CHWs who received at least one supervisory contact in the prior 3 months where registers were reviewed | # of CHWs who received at least one supervisory contact in the prior 3 month where registers were reviewed | Supervisory reports/Supervision logs or visit records/CHW self-reporting (e.g., surveys or interviews) | - Physical checks/ Extraction from RHCC reporting system | 0 | 0 | 1043 | 1043 | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| # of CHWs who correctly count respiratory rate to diagnose ARI | # of CHWs who correctly count respiratory rate to diagnose ARI | MTSS reports/ District performance Assessment reports | Physical assessment/Spot checks | 0 | 0 | 1043 | 1043 | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| # of sick children recommended for referral who are received at referral facility | # of sick children recommended for referral facility | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from DHIS2 | 0 | 0 | TBD | TBD | TBD | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| # of CHWs who are providing iCCM services one year after deployment | # of CHWs who are providing iCCM services one year after deployment | - National HMIS database - National DHIS2 database - Faciity registers - CHW registers | Extraction from DHIS2 | 0 |  | 1043 |  | 2086 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
Intermediate Outcome 2.2 Increased number of Ministry of Health staff competent in use of digitised tools | Proportion of iCCM supervisor trained | Numerator: # of supervisors assigned to iCCM (at all levels of the health system) that have been trained in iCCM Denominator: # of supervisors assigned to iCCM (at all levels of the health system) | - Training attendance registers - Surveys | - Physical checks - Key informant interviews | 0 | 81 | 82 | 100 | 100 | N/A
Output 2.3.1 Integrated tools for tracking Malaria, Pneumonia and Diarrhea developed | # of disease specific tracked | Monthly data tracked for all three diseases | DHIS2 | Extraction from DHIS2 | 0 |  | 0 | 0 | 0 | N/A |  |  | Tool developed and currenlty being tested
| # of CHW and facility phones procured | Tracking of mobile phones procured | Inventory, | - Physical checks | 0 | 266 | 0 | 0 | 266 | 266 |  |  | Mobile phones procured and ready for deployment
Intermediate Outcome 3.1 Improved advocacy and resource mobilization in RHCC districts | # of Rotarians participating in advocacy and resource mobilisation activities in RHCC districts | Number of Rotarians who participated in advocacy and resource mobilization for iCCM interventions in RHCC districts | Training attendance registers | - Monthly data reviews | 0 | 100 | 100 | 100 | TBD
Output 3.1.2: Rotarians and RHCC Country Committee participate in Global Fund commodity stakeholder meetings | Medicine and diagnostic availability | Percentage of iCCM sites with all key iCCM medicines and diagnostics in stock during the last day of reporting period Numerator: # of iCCM sites with all key iCCM medicines and diagnostics in stock during the last day of a reporting period. Denominator: # of iCCM sites assessed | - DHIS2 | - Extraction from DHIS2 | 0 | 100 | 100 | 100 | 100 | N/A |  |  | In period under review The project trainings and service provision had not commenced hence we can attribute any changes in the indicator to the project
| # of policy dialogues attended | # of policy dialogue attended to secure commitments for CHW integration and continued supply of commodities | Reports, minutes | Physical checks | [5 empty] | N/A |  |  | No policy dialogues were held since the project key deliverables were not completed
| # of Rotarians participating in stakeholder meetings | Number of Rotarians participating in National Malaria Elimination Programme meetings | - Training attendance registers | - Physical checks | 0 | 12 | 12 | 12 | TBD | N/A |  |  | No stakeholders meetings held in the period under review as key deliverables [trainings and CHW service provision were not executed
Output 3.1.4 Rotary represented on provincial-level End Malaria Councils to leverage private sector support | # of subnational End Malaria Council with rotarian representations in RHCC sites | # of subnational End Malaria Council with rotarian representations in RHCC sites | Reports, minutes | Physical checks |  | 2 | 2 | 2 | TBD | 0
Output 3.1.7: Rotarians trained in the Alma Scorecard for Surveillance & Data Monitoring | # of rotarians trained | # of Rotarians Trained | - DHIS2 | - Extraction from DHIS2 | 0 |  |  |  |  | 0 |  |  | No training was planned in the period under review
| Proportion of surveillance reports generated by trained Rotarians | # of surveillance reports generated/ The expected | - DHIS2 | - Extraction from DHIS2 | [5 empty] | 0 |  |  | No surveillance reports were generated in the period under review
Output 3.1.8: Advocacy members trained in RHCC | # of Advocacy members trained | # of Advocacy members trained in RHCC | Reports, minutes | Physical checks | [5 empty] | 0
| # of Rotary President-Elects (PEs) trained on Advocacy and RHCC | Number of Rotary President-Elects (PEs) trained on Advocacy and RHCC | Reports, minutes | Physical checks | [5 empty] | 0
| # of advocacy activities initiated by trained members | Number of activities initiated by trained members | Reports, minutes | Physical assessment/Spot checks | [5 empty] | 0
Output 3.1.6: Participated in National Campaigns and Rotary Family Health Days | # of National Campaigns campaigns participated by rotarians | Number of campaigns participated Total held | Reports, minutes | Physical assessment/Spot checks | [5 empty] | 0
| # of family health days participated by rotarians | Number of family health days participat | Reports, minutes | Physical assessment/Spot checks | [5 empty] | 0
Note on F18: Wongani Zulu: No CHWs have been trained yet
Note on F23: Wongani Zulu: No CHWs have been trained yet
Note on D25: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on F25: Wongani Zulu: TBD
Note on K25: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on D38: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on F38: Wongani Zulu: No iCCM+-trained CHWs exist yet
Note on K38: Wongani Zulu: Assumes non-malarial diseases will be added to Malaria Rapid Reporting System
Note on M38: Wongani Zulu: To only be reported when data is collected
Note on J64: Wongani Zulu: All supervisors assigned to mentor CHWs in iCCM+ should have been trained prior to their assignement as supervisors
Note on F68: Wongani Zulu: Yet to be determined
Note on F72: Wongani Zulu: Yet to be determined